## tasks and teams
Task	Priority / timeline	Weight	Deadline	orga	venue	promo	design	speakers	A/V	software	network
Decision on conf-management software	1	1		1				1		1
Find keynote(s)	2	1		1				1
Gather program suggestions from own org team	2	1		1
Cooperation with other confs during oSC15 (NLUUG/Kolab)	2	1		1
Social events planning/venues	2	2		1
Speaker guidelines	2	3		1				1
Program layout / visuals human readability check	3	3		1		1		1
Emergency contacts	3	4		1	1	1	1	1	1	1	1
Registration closing	3	4		1						1
Finalize program	3	4		1				1
Sponsor dinner	3	4		1
Welcome drink/party	3	4		1
Volunteer party	4	1		1
Party pricelist	4	1		1		1	1
GPG keysigning party	4	1		1
Partners tour	4	1		1
Organize city excursion on Sunday afternoon	4	2		1
Cookout and/or party	4	3		1
Involve tourist board The Hague	1	1		1		1
Promote oSC in SUSE offices and at SUSE events	1	2		1		1
Involve SUSE in promotion towards partners	1	2		1		1
Call for Volunteers	2	1		1		1	1
Define sponsorship packages	2	2		1
Code of conduct	3	2		1
Announce dates	1	1		1		1
Volunteers form	2	3		1
openSUSE Beer	3	1		1
List of contact people (technique/facilities) for venue	3	3		1
SUSE Payment for venue/facility suppliers	3	4		1
Provide schedule to video team	3	4		1				1	1
Assign chairmen to rooms	4	1		1
Certification exams (?)	2	1		?
Decide on uncon?	2	4		?
Organize business track	2	2		?
Promocube	3	1		?
LPI exam info (?)	3	2		?
Proofreading of texts	3	3		?
Geeko money	4	2		?
Themes per day or track?	2	1						1
Call for papers opening (announcement)	2	2				1		1
Keynote speaker interviews	2	4				1		1
Registration opening	3	1						1		1
Info on arrival date/time	3	1						1
Program in web format	3	1						1		1
Announce program	3	1				1		1
Policy on av recording	3	1							1
Speakerinfo on website	3	1						1		1
Call for papers closing (announcement)	3	1				1		1
Open Bof Suggestions	3	1						1
Program in printing format	3	2				1
Schedule Program	3	3						1
Pre registration to workshops	3	3								1
Session recording infrastructure arranged	3	3							1
Create small program to be printed on badge(?)	3	4				1	1
Onsite donations handling	4	1			1
Split videofeeds into sessions	4	4							1
Link session videofeeds to program	4	4							1
Upload all videos to YouTube	4	4							1
Lists of social media messages for promo	1	1				1
Website for conference	1	1				1	1			1
Twitter account posting management	1	1				1				1
Google+ and Facebook event pages	1	1				1
LinkedIn group?	1	1				1
Official Conference announcement	1	1				1
Keep forums up to date and answered	1	2				1
Keep (local/global) communities updated on progress	1	2				1
Conference FAQ	1	2				1
Sponsorship by city of The Hague?	1	2				1
Publish and promote CfP, Registration, Accommodation and support links	1	2				1		1
Media partners (suggestions)	1	2				1
Promo in other conferences?	1	2				1
Venue promotional article	1	3				1
Create social media memes	1	3				1
Ask SUSE for promo material	1	3				1
Create promo videos	1	3				1			1
Enable Paper submission feature on website	1	3								1
Logo proposal for conf	1	3					1
Lists of social media messages about talks accepted	1	4				1		1
Info on The Hague/NL	1	4				1
Press kit	1	4				1
Mascot for the event (?)	2	1				1	1
Flyer design (also for handouts at local events)	2	1				1	1
Motto/theme for conference	2	1				1
Online banners/badges	2	1				1	1
JoinUp announcements	2	1				1
Involve community in promotion	2	1				1
Invitation letters	2	2				1
Hotel partnershipannouncement	2	2				1
Sponsor brochure	2	2				1	1
T-shirts for promotion	2	2				1	1
QR Code stickers (?)	2	2				1
Flyer design (also for handouts at local events)	2	2				1	1
Hotel and travel info on website	2	3				1				1
Website and OSEM should feature same info on speakers	2	4						1
Information for students and travel support	2	4				1
Information about visa	2	4				1
Create datacard for badge	3	1				1				1
Design badges	3	1				1	1
Design Press badge (see program)	3	1				1	1
Countdown button for websites	3	1								1
Register now button for websites	3	1								1
Accomodation and traveling costs	3	1						1
Photo's from The Hague with Geeko's	3	1				1
openSUSE TV trailers (based on previous vids)	3	1					1		1
Put banner on opensuse.org	3	1				1	1			1
Check for cancelled speakers/sessions	3	2						1
Android app	3	2				1	1			1
Setup schedule in OSEM	3	2						1
Articles about sneak peaks for program/keynote/venue	3	2				1
Venue/city map	3	3			1
Produce conference stickers	3	4				1	1
Texts for daily newspaper	3	4				1
Sync OSEM signups with registration	3	4								1
Buttons/swag?	3	4				1	1
Rollup banner design	3	4				1	1
Poster design	3	4				1	1
Collect comments/feedback from social media (with source)	3	4				1
Create a know-how about oSC for wiki(?)	3	4				1
Print the program	3	4				1
Info about local transport	3	4			1
Keep visitors informed during conference	4	1			1	1
Print press badges	4	1				1
Sings and banners (routing) for rooms in venue	4	1				1	1
Posters for volunteer party	4	1				1	1
Household message list	4	1				1
Photo upload platform	4	1								1
Theme song (?)	4	1				1	1
T-shirts for volunteers/org	4	1				1	1
T-shirts for Attendees	4	1				1	1
Conference bags/swag (backpack?)	4	1				1
Central image inventory location	4	1								1
Print signage / routing	4	1			1	1
Joind.in talks registration	4	1						1
Questionnaires / survey	4	3				1
Thank you article	4	4				1
Collect reviews and photos for wiki	4	4				1
Venue photo's and details	1	1			1	1
Requirements/registration/contract	1	2			1
Route to venue	2	1			1
Update FAQ with venue/rooms info	2	2			1
FSFE@osc15 (?)	2	2
Attendance certificate	2	3
Room names	2	3				1	1
Inflatable openSUSE Penguins	3	2				1
Photo's/images based on room names	3	2				1
On-site extras and security measures	3	3			1
Named badges	3	3			1	1	1
Venue decorations	3	3			1	1	1
Gather necessary equipment	3	3								1	1
Big banner for entrance	3	3			1		1
Coordination with venue technicians	3	3			1				1		1
Static network documentation	3	4									1
Registration desk	3	4			1
Signs for rooms and routing	3	4				1	1
IRC channel per room and ensure room chairs have access	3	4								1	1
Food suggestions during event	3	4			1
Artwork pieces	3	4					1
Free maps of The Hague	3	4			1	1
Meeting about cabling and network equipment	3	4							1		1
Get photographers for the event	3	4				1
Floor plan for venue	3	4			1
Seating in lobby	3	4			1
Seating in conference rooms					1
Pricelist for consumptions	4	1			1	1	1
Infrastructure test	4	1							1		1
Video recording and streaming	4	1							1
openSUSE Booth	4	1			1
Volunteers training	4	1			1
Network setup	4	1							1		1
Garbage bags	4	1			1
Beers and refreshments	4	1			1
Storage room(s)	4	1			1
Check video equipment and dvswitches	4	1							1
Coffee/tea/water at strategic points (rooms)	4	1			1
Location for booths	4	1			1
Put postit geekos on windows	4	2			1
Collect videos	4	3							1
Aftermovie	4	4				1			1
Thank you letter for speakers	4	4						1